## Slide 1: Having Fun with
Applied Computing Slideshows
by Mark Kelly
vcedata.com
mark@vcedata.com
Gantt

## Slide 2: Well, “fun” might be optimistic
At least they’re more fun than this…

## Slide 3: What is Gantt?
Gantt charts :
are timelines
manage the tasks involved in big and complex projects
let project managers organise time, people, equipment and money
ensure the right people and equipment are in the right place and the right time

## Slide 4: What is Gantt?
Gantt charts :
allow managers to monitor the progress of a project
are adjusted to reflect actual project progress

## Slide 5: Gantt Charts
Henry Laurence Gantt (1861-1919)
Gantt Charts

## Slide 6: Gantt Charts
Henry Laurence Gantt (1861-1919)
Gantt Charts
And please spell my name right.
It’s Gantt.
Not ‘Gannt’.
Not GANTT.

## Slide 7: Gantt Charts
Henry Laurence Gantt (1861-1919)
Gantt Charts
Thanks.
And did you know that Gantt charts are a huge hit at parties?

## Slide 8: Gantt Charts
Henry Laurence Gantt (1861-1919)
Gantt Charts
Call me.

## Slide 9: How much do you need to know?
The study design requires you to have a basic understanding of project management concepts.
You need to be able to create and modify a simple Gantt chart with software.
You do not have to know anything about PERT charts (another common project management tool)

## Slide 10: Gantt Basics
Basically, a timeline with tasks that can be connected to each other

## Slide 11: Making a Gantt chart
Step 1 – list all of the tasks in the project

## Slide 12: Making a Gantt chart
Step 2 – add task durations.

## Slide 13: Making a Gantt chart
Skill and industry-experience guide the choice of task durations.
But real-world events usually mess with predicted durations…

## Slide 14: Making a Gantt chart
Charts must be adjusted to reflect real-world progress.
Your SAC must contain evidence of such adjustments.

## Slide 15: Making a Gantt chart
Using the right software makes chart adjustments easy.
More on software choices later…

## Slide 16: Making a Gantt chart
Step 3 – add dependencies (the tasks that cannot start before another task finishes)

## Slide 17: Dependencies
The arrows indicate dependencies.
Task 1 is a predecessor of task 2 – i.e. task 2 cannot start before task 1 ends.
Task 3 is dependent on task 2. Task 7 is dependent on two other tasks
Electrics, plumbing and landscaping are concurrent tasks and can happen at the same time, so they overlap on the chart. All 3 can start after task 4 ends.
Painting must wait for both electrics and plumbing to be finished.
Task 9 has zero duration, and is a milestone

## Slide 18: Scope in 2016-2019
You need to know the terms dependency and milestone.
The term predecessor is handy to know, but probably won’t appear on the exam.
Know the terms critical path and slack time, just in case.

## Slide 19
Slack is the amount of time a task can run overtime before it affects other tasks.
Task 6 can take an extra day and a half before it affects the project’s end date, so each has 1.5 day’s slack.
If a task runs overtime and it has no slack, the start dates of following tasks will be affected.

## Slide 20
The diamond shape indicates a milestone.
Used to monitor whether a project is on schedule or not. E.g. “The enter project must be finished by 9 September.”
A milestone is an event, not a task – a point of major progress in the project. It has ZERO duration.
i.e. nothing must be done to achieve it – it just HAPPENS because of previous stuff happening.

## Slide 21: Milestones
Milestones are events, not tasks – they happen, but no time or work is required to accomplish them.
They are points of major progress in the project.
They usually refer to the start or end of major tasks or groups of tasks.
The end-date is the major milestone of any project.
Milestones are created as tasks with zero duration and no resources (e.g. staffing).

## Slide 22: Real Exam Questions
Informatics 2016 – A11
For the Gantt chart shown above, a delay in the completion of Task D by one day will
a. have no effect on Task E.
b. delay only Task E by one day.
c. delay only Task F by one day.
d. delay both tasks E and F by one day.

## Slide 23: Real Exam Questions
Informatics 2016 – A11
For the Gantt chart shown above, a delay in the completion of Task D by one day will
a. have no effect on Task E.
b. delay only Task E by one day.
c. delay only Task F by one day.
d. delay both tasks E and F by one day.
Answer is A. Why?

## Slide 24: 2003 Exam Multichoice Q16
Is Task D is a predecessor for :
(A) Tasks E & F?
(B) Tasks B & C?
(C) Tasks C & F?
(D) Tasks B & E?

## Slide 25: 2003 Exam Multichoice Q16
No dependency arrows – be prepared for this in exam questions.
Assume that any task that does not start on day 1 must be dependent on some other task.
Which tasks are dependent on task D?
Find the tasks that start as soon as task D has finished… E and F. So the answer is [A].

## Slide 26: Gantt tools
Study design says that Gantt charts (‘project plans’) must be created with software. Not hand-drawn!

## Slide 27: Gantt tools
Excel is possible but NOT recommended.
  Dependency arrows are nearly impossible.
  Updating charts is a major pain because tasks are not logically connected. Changing one task means manually adjusting several others.
 Yuk!

## Slide 28
GanttProject (free) at ganttproject.biz
(still working in 2024)
    A nice, simple tool. Lacks a few fancy features (e.g. allowing different working hours for different tasks) but will suit all VCE needs.

## Slide 29
  Microsoft Project.
    Big, fully-featured, $$$

## Slide 30
Online Gantt creators
  Dozens of sites exist, e.g. Ganttpro.com, smartsheet.com
  Many are free.
  Problem: charts are not portable, and must be saved and edited on the site.
  Need internet access.
 smartsheet.com

## Slide 31: Because you’ve been good

## Slide 32: Thanks
Applied Computing Slideshows
by Mark Kelly
vcedata.com
mark@vcedata.com